## Slide 1
Organising a Club Dive Trip
From first idea to everyone home
A practical session for members and prospective Dive Leaders
UK WEEKEND EXAMPLE • OVERSEAS VARIATIONS

## Slide 2
SESSION ROUTE
A successful trip is planned from the people outwards
STAFFORDSHIRE DIVERS
02
BY THE END
Define the outcome. Match the diving to the people attending.
Separate the roles. Organising logistics is not the same as managing diving.
Commit in stages. Know the numbers, terms and alternatives before money moves.
Plan the day. Prepare the programme, records and emergency arrangements.
Close the loop. Bring back every person, every item—and a balanced account.
The checklists in this deck are practical working templates—not official BSAC forms.
MAIN WORKED EXAMPLE
UK
COASTAL WEEKEND
Eight club members plan two days of coastal diving.
THEN APPLY THE SAME METHOD
OVERSEAS TRIP
The planning framework stays the same.

## Slide 3
OPENING DISCUSSION
What could stop a trip—even when the weather is perfect?
STAFFORDSHIRE DIVERS
03
“
A trip fails long before the forecast if a critical dependency was never confirmed.
NO MANAGER
No suitable Dive Manager
NO GAS
Fills unavailable
NO BUDDIES
Too little experience
NO BOAT
Booking never confirmed
NO PLAN B
Conditions change
Successful outcome: suitable diving • clear costs • prepared logistics • workable alternatives • everyone home

## Slide 4
AGREE ROLES EARLY
Members can organise the trip without managing its diving
STAFFORDSHIRE DIVERS
BSAC: Safe Diving — Dive management
04
ROLE | MAIN RESPONSIBILITY
Trip organiser | Bookings, participants, travel, accommodation, costs and communication
Diving Officer | Authorises branch diving and appoints a suitable Dive Manager
Dive Manager | Plans and oversees the diving activities
Assistant Dive Manager | Takes agreed duties and covers handovers
Skipper / coxswain | Safe operation of the boat
Instructors | Agreed training within their qualifications
Individual divers | Fitness, equipment, capability and agreed dive plan
The organiser and Dive Manager may be the same person—if they are suitable for both roles.

## Slide 5
OLDER DIVE LEADER SYLLABUS (2009)
DP1 and DP2 developed dive management—not holiday organisation
STAFFORDSHIRE DIVERS
05
DP1
DIVE MANAGEMENT 1
Shadow an instructor
Participate in preparing and managing a day’s diving at a site known to the branch.
→
DP2
DIVE MANAGEMENT 2
Take the lead
Plan and manage the diving, with the instructor providing support.
DP2 evidence
identify what is needed
prepare beforehand
address site safety
monitor diving
delegate effectively
SCOPE
A day’s dive-management exercise at a known site
—not a requirement to organise a residential weekend or overseas holiday.
Check the exact instructor-manual edition before treating participant or dive numbers as prescribed requirements.
Sources: older qualification record (Prima Sub-Aqua); published practical objectives (LSAC); BSAC Dive Manager guidance

## Slide 6
CREATE CLEAN HANDOVERS
Make the organiser–DO–Dive Manager boundary explicit
STAFFORDSHIRE DIVERS
BSAC: Safe Diving — Dive management
06
TRIP ORGANISER
ORGANISES
• people & communications
• suppliers & travel
• costs & records
→
DIVING OFFICER
AUTHORISES
• branch activity
• suitable Dive Manager
• club oversight
→
DIVE MANAGER
MANAGES
• dive plan & briefing
• risk and conditions
• monitoring & records
An explicit handover matters whenever responsibility changes during the day.

## Slide 7
BEFORE MONEY MOVES
Write a one-page proposal and test feasibility with the Diving Officer
STAFFORDSHIRE DIVERS
07
THE PROPOSAL
Destination + date window
Purpose / objective
Expected depth + conditions
Intended participants
Shore diving or charter boat
Approximate group size
Indicative total cost
Alternative sites
Organiser + proposed dive management
EXAMPLE
Two days of coastal diving for eight members, with sites suitable for the confirmed group and sheltered alternatives.
Decision at this stage
Worth researching—not yet worth booking.

## Slide 8
WORKED EXAMPLE
A UK coastal weekend exposes the decisions in the right order
STAFFORDSHIRE DIVERS
08
8
members
Group: two recently qualified Ocean Divers; one equipment-hire request.
Platform: charter for eight divers.
Constraint: fill station closes at 5 pm.
Uncertainty: forecast may rule out preferred sites.
Aim: two days’ diving with sheltered alternatives.
BEFORE BOOKING
• Who can manage the diving?
• What sites fit the group?
• Can the gas plan work?
• What is the minimum viable number?
• What happens if Plan A is lost?
Use this example throughout the session

## Slide 9
BUILD AROUND THE REAL GROUP
A qualification card is only one part of the assessment
STAFFORDSHIRE DIVERS
09
EVIDENCE TO GATHER
• Qualifications + additional training
• Recent diving in similar conditions
• Depth experience
• Dry suit / boat / current / DSMB experience
• Confidence + support needed
• Equipment availability
• Training requests
RECENCY
Can matter as much as the grade on the card.
BUDDYING
Identify experienced buddies and supervision needs early.
TRAINING
Agree the instructor, scope and time before the trip.

## Slide 10
RESEARCH EVERY POTENTIAL SITE
Local knowledge turns information into a usable plan
STAFFORDSHIRE DIVERS
BSAC: Safe Diving — Seamanship
10
INFORMATION | QUESTIONS TO ANSWER
Access | Permission, parking, fees, hours and carrying distance?
Diving | Depth, seabed, visibility, current and main hazards?
Tides | Is slack required—and what reliable local information establishes it?
Exposure | Which wind directions and swell affect the site?
Entry / exit | Can divers enter and recover safely as conditions change?
Facilities | Toilets, shelter, gas, storage and food?
Emergencies | Communications, casualty recovery and emergency access?
Alternatives | What nearby site suits different conditions?
For an unfamiliar location, combine charts, tides and forecasts with people who know the site.

## Slide 11
PLAN BACKWARDS FROM THE DIVING DAY
The timeline gets more specific as commitment increases
STAFFORDSHIRE DIVERS
11
1
3–12 months
Proposal • DO discussion • research • indicative costs
2
Before money
Management • viable numbers • supplier terms
3
1–3 months
Participants • bookings • transport • gas
4
2–4 weeks
Risk assessment • EAP • joining instructions
5
Final week
Reconfirm • equipment • monitor weather
6
Each day
Conditions • briefing • records • handovers
7
After return
Equipment • finances • records • review
The booking deadline—not habit—sets the real planning lead time.

## Slide 12
SHOW THE WHOLE COST
Separate shared expenses from personal costs
STAFFORDSHIRE DIVERS
12
SHARED EXPENSE | ILLUSTRATIVE AMOUNT
Charter | £1,200
Accommodation | £800
Other shared costs | £200
TOTAL | £2,200
Cost each: 8 paying participants | £275
SHOW SEPARATELY
• Travel / ferries / parking / tolls
• Launching, mooring and boat fuel
• Air, nitrox and equipment hire
• Site fees or permits
• Food arrangements
• Personal equipment needs
Add only an explicitly agreed contingency
Illustrative calculation supplied for the session—not a current quote.

## Slide 13
MAKE THE FINANCIAL RULES VISIBLE
A deposit should follow clarity—not create it
STAFFORDSHIRE DIVERS
13
BEFORE TAKING MONEY
What is included / excluded
Deposit and balance dates
Cancellation and refund terms
Minimum viable number
Supplier cancellation terms
Who can authorise a shortfall
IF THINGS CHANGE
A participant withdraws: apply the written terms consistently.
The boat cancels: follow supplier terms and tell members quickly.
Numbers fall: recalculate before creating an unapproved deficit.
Conditions change: safety decisions remain separate from sunk cost.
Record the decision and the person authorised to make it.

## Slide 14
KEEP ONE CONTROLLED PARTICIPANT REGISTER
Names, capability and payments need one current record
STAFFORDSHIRE DIVERS
BSAC: Planning a club trip abroad
14
PARTICIPANT DETAILS
• Name + contact details
• Qualification + relevant experience
• Equipment / hire requests
• Emergency contact
• Fitness documentation confirmed
MONEY + COMMUNICATION
• Deposit paid
• Balance due
• Inclusions and exclusions
• Deadlines and cancellation terms
• Club payment process
NEED TO KNOW
Keep sensitive information accessible only to those who need it.
Keep one payment record—not parallel spreadsheets and chat threads.

## Slide 15
PLAN THE NON-DIVING DAY TOO
Travel and accommodation can decide whether the dive plan works
STAFFORDSHIRE DIVERS
BSAC: Planning an expedition
15
TRAVEL
• Drivers, passengers and kit capacity
• Realistic journey + rest breaks
• Secure cylinder transport / loading
• Ferries, tolls and parking
• Trailer access and manoeuvring
ACCOMMODATION
• Arrival, keys and late check-in
• Wet kit storage and drying
• Breakfast versus departure times
• Accessibility and dietary needs
• Appropriate welfare for under-18s
Test the timings: arrival → kit prep → departure → fills → dinner → rest

## Slide 16
TREAT GAS AS A SUPPLY CHAIN
Know the source, capacity, turnaround and fallback
STAFFORDSHIRE DIVERS
16
QUESTIONS BEFORE TRAVEL
• Where are fills available?
• Which gases and pressures?
• Opening hours and turnaround?
• Cylinder inspection evidence?
• Can the supplier serve the group?
• How many cylinders per diver?
• Fallback if fills are unavailable?
NAME THE CARRIER
SHARED ITEM | NAMED PERSON
Oxygen equipment | ____________
First-aid kit | ____________
Communications | ____________
Dive records | ____________
Shared spares / tools | ____________
Hired club equipment | ____________
Nitrox / technical gas: analyse, label and complete personal gas planning.

## Slide 17
MAKE RISK ASSESSMENT SPECIFIC
Start generic—then add the site, activity and today’s conditions
STAFFORDSHIRE DIVERS
BSAC: Risk assessment resources
17
HAZARD | POSSIBLE CONTROLS
Slippery shore access | Inspect route • suitable tide • assistance
Strong current | Reliable local advice • timing • suitable divers • recovery
Cold / fatigue | Protection • shelter • rest • realistic programme
Poor communications | Test coverage • appropriate alternative
Boat failure | Maintenance checks • communications • recovery plan
Review whenever the site, people, platform or conditions change.
Purpose: prevent incidents and show that significant hazards and controls were considered.

## Slide 18
BUILD THE EMERGENCY PLAN AROUND THREE QUESTIONS
Who acts, where is the equipment, and how does help reach the casualty?
STAFFORDSHIRE DIVERS
BSAC: Seamanship + current incident procedure
18
WHO
• response coordinator
• first aid + oxygen
• meets emergency services
• monitors remaining divers
WHERE
• exact location / coordinates
• access + landing points
• oxygen / first aid / records
• casualty details kept
HOW
• primary + backup alarm
• recover injured diver
• evacuate to professional care
• close remaining diving
Check oxygen quantity against time to professional care—including delays.
At sea around the UK, the supplied BSAC guidance identifies marine VHF / DSC as the primary emergency call method.

## Slide 19
BUILD SLACK INTO THE DIVING PROGRAMME
A packed schedule creates pressure to rush or continue
STAFFORDSHIRE DIVERS
BSAC: Safe Diving — Dive management
19
ARRIVE
Travel • keys • kit
PREPARE
brief • loads • gas
CHECKOUT
if appropriate
DIVE
site / buddy / waves
RESET
surface interval • fills
ALTERNATIVE
Plan B / training
RECOVER
kit • records • return
The Dive Manager considers capability, fitness, depth limits, platform and emergency backup.
Time pressure is a planning defect—not a reason to compromise.

## Slide 20
PRE-PLAN THE WEATHER DECISION
Plan A, Plan B and Plan C keep sunk cost out of the safety call
STAFFORDSHIRE DIVERS
20
PLAN A
Preferred diving
PLAN B
Suitable sheltered alternative
PLAN C
Other activity or cancellation
AGREE IN ADVANCE
• Who decides—and by when?
• When will participants be updated?
• Who contacts suppliers?
• What happens to payments?
• What limits matter for journey, launch, entry, exit and recovery?
DISCUSS
The charter is paid—but recovery conditions are unsuitable.
What happens?
Safety and capability still decide.

## Slide 21
SEND ONE DEFINITIVE JOINING DOCUMENT
Members should not need to reconstruct the plan from messages
STAFFORDSHIRE DIVERS
21
GET THERE
• meeting place + time
• map / parking / contacts
• travel + accommodation
• delay / withdrawal process
GET READY
• outline programme
• kit + cylinders
• gas arrangements
• food + supplies
STAY CURRENT
• outstanding payments
• documents to bring
• weather decision deadline
• offline copy
Keep the current version available offline.

## Slide 22
BRIEF, MONITOR, HAND OVER AND CLOSE
Dive records make the plan visible while people are underwater
STAFFORDSHIRE DIVERS
BSAC: Safe Diving — Dive management
22
BRIEF THE GROUP
• site, conditions and hazards
• roles and buddy arrangements
• entry, exit and recovery
• depth / time / gas / decompression
• separation and emergency procedures
• signals and recall
RECORD + MONITOR
Before entry: buddy pairs, entry time, expected duration.
While diving: monitor progress and identify overdue pairs.
On exit: confirm everyone is out and well.
Afterwards: record actual details and problems.
At handover: name the person now monitoring the diving.
The handover is explicit—not assumed.

## Slide 23
OVERSEAS ADDS BORDERS, OPERATORS AND DISRUPTION
Clarify what the club owns—and what the local operator owns
STAFFORDSHIRE DIVERS
BSAC: Planning a club trip abroad
23
BEFORE BOOKING
Passport / entry requirements
Qualification recognition
Local diving rules
Insurance: diving + evacuation + treatment
Hire kit + cylinder compatibility
Airline equipment rules
Transfers + disruption
No-fly / altitude intervals
Verified emergency support
RESPONSIBILITY SPLIT
CLUB
people • preparation • records • communication
OPERATOR
local platform • site operation • local emergency arrangements
Write down the interface.

## Slide 24
THE TRIP ENDS AFTER THE ADMIN CLOSES
People, equipment, finances and learning all need an owner
STAFFORDSHIRE DIVERS
24
PEOPLE
• everyone returned
• shore contact closed
• incidents / near misses
EQUIPMENT
• clean + dry + return
• faults reported
• boat recovered
FINANCES
• invoices settled
• refunds completed
• records balanced
LEARNING
• dive / training records
• supplier + site notes
• agreed report + photos
What would you change before running this trip again?

## Slide 25
CHECKLIST 1
Before committing money
STAFFORDSHIRE DIVERS
25
Purpose, dates and intended participants agreed
Feasibility discussed with the Diving Officer
Suitable diving management identified
Diving appropriate for the likely group
Main sites and alternatives researched
Gas availability checked
Complete estimated costs circulated
Minimum numbers and cancellation terms understood
Deposits and financial responsibilities agreed
Practical working template—not an official BSAC form.

## Slide 26
CHECKLIST 2
Before departure
STAFFORDSHIRE DIVERS
26
Branch authorisation and Dive Manager confirmed
Participant capability and documentation checked
Bookings, balances and contacts confirmed
Transport and accommodation finalised
Gas and equipment allocated
Risk assessment and emergency plan reviewed
Oxygen, first aid and communications checked
Surface and shore-contact arrangements agreed
Joining instructions issued
Weather decision and alternatives communicated
Practical working template—not an official BSAC form.

## Slide 27
CHECKLIST 3
Before diving starts
STAFFORDSHIRE DIVERS
27
Actual conditions assessed
Entry, exit and recovery checked
Divers fit and ready
Buddy pairs and individual plans agreed
Briefing completed
Emergency equipment accessible
Communications checked
Dive recording and monitoring ready
Everyone knows who is managing the diving
Anyone can raise a concern or withdraw
Practical working template—not an official BSAC form.

## Slide 28
CHECKLIST 4
Before leaving the site
STAFFORDSHIRE DIVERS
28
All divers accounted for and checked for problems
Dive records completed
Equipment and boat recovered
Relevant contacts told diving has finished
Faults or incidents recorded
Next arrangements communicated
Do not let the last person leave with an open task nobody owns.
Practical working template—not an official BSAC form.

## Slide 29
SMALL-GROUP EXERCISE
Turn the coastal-weekend scenario into a viable trip
STAFFORDSHIRE DIVERS
29
8 members • 2 recent Ocean Divers • 1 hire request • 8-seat charter • fills close 5 pm • uncertain forecast
PRODUCE
1 Short trip proposal
2 Questions before booking
3 Realistic budget
4 Diving + support rota
5 Weather alternative
6 Outline emergency plan
Work in groups • compare plans • agree next actions

## Slide 30
CLOSE THE LEARNING LOOP
A repeatable method matters more than a perfect destination
STAFFORDSHIRE DIVERS
30
FIRST IDEA
Clarify purpose, people and constraints.
COMMIT
Confirm authority, numbers, terms and alternatives.
DIVE
Brief, monitor, adapt and hand over.
HOME
Close people, kit, money and learning.
“What would you change before running this trip again?”
A well-organised trip is one people feel ready for, can afford—and want to repeat.

## Slide 31
KEEP THE SOURCE MATERIAL CURRENT
Useful BSAC references
STAFFORDSHIRE DIVERS
31
01
Safe Diving: Dive management
www.bsac.com/safety/safe-diving-guide/dive-management/
02
Dive planning resources
www.bsac.com/advice-and-support/dive-planning/
03
Risk assessment resources
www.bsac.com/advice-and-support/dive-planning/risk-assessments/
04
Safe Diving: Seamanship
www.bsac.com/safety/safe-diving-guide/seamanship/
05
Planning a club trip abroad
www.bsac.com/advice-and-support/scubatravel/feature-from-sept-scuba-booking-club-hols/
06
Planning an expedition
www.bsac.com/advice-and-support/expedition-diving/planning-an-expedition/
Use the current online guidance and verified local emergency information.